## Sheet1
Milestones | Plan | Target | Mechanical Design | Software | Hardware | Deadline | Tasks | Survey Responsibility
Mobile Robot Manufacturing | - Manufacturing a ready-made design - Get the hardware Componets | Make 3 robots minimun | 3D Printed / Laser Cutting based on the design | N/A | N/A | 2020-02-05 | - Get the design - Manufacturing and assembling the robot | Amira
Low Level Control | - Decide the microcontroller used for the Low Level Control - Writing the Robot Navigation Algorthim | Making a valid algorithm as an abstraction layer for low level control | N/A | Robot Navigation / Obstacle Detector / Robot Feautures | (To be comfirmed) - Atmega32 - 2 Dc Motors / robot - DC Motor Driver / robot - Obstacle Avoider Sensor (UltraSonic) - Battery / robot - Safety Circuit | 2020-02-05 | - Get the hardware componenets needed - Write the Software | Salma
Integration Milestone 1 &2 | N/A | To be done on all the three robots | N/A | N/A | N/A | 2020-02-07 | - Integrate the software with the hardware and test it
Intermediate Layer | - Sensor Fusion between all the robots' sensors - Search for the communication protocol to be used to deliver the output to the high level control (ex: SPI/I2C/CAN) | Connection betwen the low level control and high level control | N/A | - Write the communication protocol driver (Plan B exsists for a read-made driver) - Sensor Fusion | N/A | 2020-02-07 | - Search for the optinum protocol - Start writing its driver - Search for the sensor fusion concept and apply it on the robots | Mido
High Level Control | - Implementing ROS on a Raspberry Pi |  | N/A |  | RaspberryPi / robot | 2020-02-14 | - Understanding ROS - Implementing each phase in Autonomous Robot through ROS | Kariman
SWARM Algorithm | - Determininng which algorithm to be used - (One Master and many Slave / Peer to Peer / ...) | Get the optinum algorithm that serves our application | N/A |  | N/A | 2020-02-14 |  | Mostafa
Communication Module between Robots | - The communication between each robot (Wifi / Bluetooth) |  | N/A |  | N/A | 107/2020 | - Search for possible modules to communicate between robots - Search for the way of its implemtation - Apply it on our algorithm | Amr
Application Layer | - Write the code for the SWARM pattern | [5 empty] | - Write the application code