## Sheet1
WBS | TASK DESCRIPTION | ASSIGNED TO | PROGRESS | PLAN START | PLAN END | PLAN DAYS | ACTUAL END | Notes
Phase 1: Surveys
| Search for Designs for the Robot | Amira |  | 1/30/20 | 1/31/20 | 1 | 1/31/20
| Seach for Sensors and Actuators needed to build a swarm | Salma |  | 1/30/20 | 1/31/20 | 1 | 1/31/20
| Search for communication protocol | Mido |  | 1/30/20 | 1/31/20 | 1 | 1/31/20
| Search for SWARM Algorithm | Mostafa |  | 1/30/20 | 1/31/20 | 1 | 1/31/20
| Search for the Communication module between robots | Amr |  | 1/30/20 | 1/31/20 | 1 | 1/31/20
| Search for implementation of ROS on a RPI | Kariman |  | 1/30/20 | 1/31/20 | 1 | 1/31/20
Phase 2: Designs Implementation